## Schedule Development
Schedule Development HRM System (Lite Modules)
RIM
Irawan Susanto
Project start date: | 2024-06-10 | [10 empty] | Scrolling increment: | [5 empty] | 0
Milestone marker: | 1 | 1 |  |  | June | [20 empty] | July
 | time axis 2024-06-10 to 2024-08-04
Milestone description | Assigned to | Progress | Start | Days | time axis 2024-06-10 to 2024-08-04
Master Data
General Database Address Location, Bank | Full Stack | 100% | 2024-06-10 | 2
Employee Religion, Nationality, Gender, Status, Family, etc. | Full Stack | 100% | 2024-06-12 | 10
Corporate Account Finance, Tax, Bank, BPJS Account | Full Stack | 100% | 2024-06-22 | 5
Time Management Calendar, Shift, Attendance Type | Full Stack | 100% | 2024-06-27 | 5
Payroll & Tax Component, Allowance, Period, Bonus, E-Slip, Tax, etc. | Full Stack | 100% | 2024-07-02 | 10
Organization
Structure manage organization, linked to employee | Full Stack | 100% | 2024-07-12 | 5
Position manage position, linked to employee | Full Stack | 100% | 2024-07-17 | 2
Function manage function, linked to employee | Full Stack | 100% | 2024-07-19 | 2
Class & Grade manage class & grade, linked to employee | Full Stack | 100% | 2024-07-21 | 2
Employee
Personal Data Manage employee info, address, family, organization, fixed salary, etc. | Full Stack | 0% | 2024-07-23 | 10
Warning Letter Manage employee warning letters | Full Stack | 0% | 2024-08-02 | 2
Import Data Importing new employee data | Full Stack | 0% | 2024-08-04 | 2
Export Data Export tool for employee data | Full Stack | 0% | 2024-08-06 | 3
Generate Tools Generating membership, position, class & grade | Full Stack | 0% | 2024-08-09 | 5
Time Sheet
Employee Shift Managing employee shift schedules | Full Stack | 0% | 2024-08-14 | 5
Daily Attendance Employee attendance, sync to att. Machine or ESS, daily allowance process | Full Stack | 0% | 2024-08-19 | 10
Overtime Form Manage proposed, actual overtime, and compile to allowance | Full Stack | 0% | 2024-08-29 | 5
Personal Leave Manage for employee annual leave and long leave | Full Stack | 0% | 2024-09-03 | 5
Payroll & Tax
Check Tools Tools for checking before and after payrol process | Full Stack | 0% | 2024-09-08 | 3
Manual Import Tools for import of manual calculation | Full Stack | 0% | 2024-09-11 | 3
Calculation Process Employee salary, daily allowance, fixed allowance, membership, and tax | Full Stack | 0% | 2024-09-14 | 10
E-Slip Salary Sending slip salary to email, and ess application | Full Stack | 0% | 2024-09-24 | 5
Salary Recap Report for monthly salary calculation | Full Stack | 0% | 2024-09-29 | 5
Report
Employee All employee report | Junior | 0% | 2024-10-04 | 5
Time Sheet All time sheet report | Junior | 0% | 2024-10-09 | 10
Payroll & Tax All salary, daily allowance, fixed allowance, membership, and tax reports | Junior | 0% | 2024-10-19 | 10
Dashboard | Full Stack
Employee Display employee info, by gender, by ages, by position, by organization, etc. | Full Stack | 0% | 2024-10-29 | 3
Time Sheet Display employee attendance statistics | Full Stack | 0% | 2024-11-01 | 3
Payroll & Tax Display employee salary statistics | Full Stack | 0% | 2024-11-04 | 3
Employee Self Services (Mobile Apps)
Dashboard Display employee (current users) information | Full Stack | 0% | 2024-11-07 | 2
Permission Employee permission propose form | Full Stack | 0% | 2024-11-09 | 2
Leave Employee leave propose form | Full Stack | 0% | 2024-11-11 | 2
Time Stamp Attendance check in and check out | Full Stack | 0% | 2024-11-13 | 2
History Employee attendance history | Full Stack | 0% | 2024-11-15 | 1
E-Slip Salary Receive E-Slip, download, and share to others apps | Full Stack | 0% | 2024-11-16 | 3
Workflow Approval Head of organization approval for members propose permisson or leave. | Full Stack | 0% | 2024-11-19 | 5
Notifications Receiving notifications for any propose or approval activity | Full Stack | 0% | 2024-11-24 | 2
Tools & Settings Change or reset password, app configuration, etc | Full Stack | 0% | 2024-11-26 | 2
Internal Testing
Testing Unit testing web and mobile apps all modules | Junior | 0% | 2024-11-28 | 5
Bug Fixing Fix all errors found in unit testing | Junior | 0% | 2024-12-03 | 10
Documentation
FSD Functional Specification Document. | Junior | 0% | 2024-12-13 | 15
Manual Book Users operation manual book | Junior | 0% | 2024-12-28 | 15
Mandays |  |  | Full Stack | 146
|  |  | Junior | 70
|  |  | TOTAL | 216

## Schedule Internal Team
Schedule Internal Team HRM System (Lite Modules)
RIM
Irawan Susanto
Project start date: | 2023-10-02 | [10 empty] | Scrolling increment: | [5 empty] | 69
Milestone marker: | 1 | 1 |  |  | December | [27 empty] | January
 | time axis 2023-12-10 to 2024-02-03
Milestone description | Assigned to | Progress | Start | Days | time axis 2023-12-10 to 2024-02-03
Master Data
General Database Address Location, Bank | Full Stack | 0% | 2023-10-02 | 2
Employee Religion, Nationality, Gender, Status, Family, etc. | Full Stack | 0% | 2023-10-04 | 2
Corporate Account Finance, Tax, Bank, BPJS Account | Full Stack | 0% | 2023-10-06 | 1
Time Management Calendar, Shift, Attendance Type | Full Stack | 0% | 2023-10-07 | 2
Payroll & Tax Component, Allowance, Period, Bonus, E-Slip, Tax, etc. | Full Stack | 0% | 2023-10-09 | 2
Organization
Structure manage organization, linked to employee | Full Stack | 0% | 2023-10-11 | 1
Position manage position, linked to employee | Full Stack | 0% | 2023-10-12 | 1
Function manage function, linked to employee | Full Stack | 0% | 2023-10-13 | 2
Class & Grade manage class & grade, linked to employee | Full Stack | 0% | 2023-10-15 | 2
Employee
Personal Data Manage employee info, address, family, organization, fixed salary, etc. | Full Stack | 0% | 2023-10-17 | 3
Warning Letter Manage employee warning letters | Full Stack | 0% | 2023-10-20 | 1
Import Data Importing new employee data | Full Stack | 0% | 2023-10-21 | 2
Export Data Export tool for employee data | Full Stack | 0% | 2023-10-23 | 1
Generate Tools Generating membership, position, class & grade | Full Stack | 0% | 2023-10-24 | 1
Time Sheet
Employee Shift Managing employee shift schedules | Full Stack | 0% | 2023-10-25 | 1
Daily Attendance Employee attendance, sync to att. Machine or ESS, daily allowance process | Full Stack | 0% | 2023-10-26 | 2
Overtime Form Manage proposed, actual overtime, and compile to allowance | Full Stack | 0% | 2023-10-28 | 2
Personal Leave Manage for employee annual leave and long leave | Full Stack | 0% | 2023-10-30 | 2
Payroll & Tax
Check Tools Tools for checking before and after payrol process | Full Stack | 0% | 2023-11-01 | 1
Manual Import Tools for import of manual calculation | Full Stack | 0% | 2023-11-02 | 1
Calculation Process Employee salary, daily allowance, fixed allowance, membership, and tax | Full Stack | 0% | 2023-11-03 | 1
E-Slip Salary Sending slip salary to email, and ess application | Full Stack | 0% | 2023-11-04 | 1
Salary Recap Report for monthly salary calculation | Full Stack | 0% | 2023-11-05 | 1
Report
Employee All employee report | Junior | 0% | 2023-11-06 | 1
Time Sheet All time sheet report | Junior | 0% | 2023-11-07 | 1
Payroll & Tax All salary, daily allowance, fixed allowance, membership, and tax reports | Junior | 0% | 2023-11-08 | 1
Dashboard | Full Stack
Employee Display employee info, by gender, by ages, by position, by organization, etc. | Full Stack | 0% | 2023-11-09 | 1
Time Sheet Display employee attendance statistics | Full Stack | 0% | 2023-11-10 | 1
Payroll & Tax Display employee salary statistics | Full Stack | 0% | 2023-11-11 | 1
Employee Self Services (Mobile Apps)
Dashboard Display employee (current users) information | Full Stack | 0% | 2023-11-12 | 2
Permission Employee permission propose form | Full Stack | 0% | 2023-11-14 | 2
Leave Employee leave propose form | Full Stack | 0% | 2023-11-16 | 2
Time Stamp Attendance check in and check out | Full Stack | 0% | 2023-11-18 | 2
History Employee attendance history | Full Stack | 0% | 2023-11-20 | 1
E-Slip Salary Receive E-Slip, download, and share to others apps | Full Stack | 0% | 2023-11-21 | 1
Workflow Approval Head of organization approval for members propose permisson or leave. | Full Stack | 0% | 2023-11-22 | 1
Notifications Receiving notifications for any propose or approval activity | Full Stack | 0% | 2023-11-23 | 1
Tools & Settings Change or reset password, app configuration, etc | Full Stack | 0% | 2023-11-24 | 1
Internal Testing
Testing Unit testing web and mobile apps all modules | Junior | 0% | 2023-11-25 | 5
Bug Fixing Fix all errors found in unit testing | Junior | 0% | 2023-11-30 | 10
Documentation
FSD Functional Specification Document. | Junior | 0% | 2023-12-10 | 5
Manual Book Users operation manual book | Junior | 0% | 2023-12-15 | 5
Mandays |  |  | Full Stack | 51
|  |  | Junior | 28
|  |  | TOTAL | 79